## Sheet1
Name | Stage | StartDate | EndDate | Dependencies | Resources | IsMilestone
Architecture Review | EVT | 2024-03-01 | 2024-03-04 |  | EE Manager | FALSE
Schematic Design | EVT | 2024-03-05 | 2024-03-19 | Architecture Review | EE Engineer A | FALSE
PCB Layout | EVT | 2024-03-20 | 2024-04-09 | Schematic Design | Layout Team | FALSE
Long Lead Component PO | EVT | 2024-03-01 | 2024-04-15 |  | Purchasing | FALSE
PCB Fabrication | EVT | 2024-04-10 | 2024-04-19 | PCB Layout | Vendor X | FALSE
SMT Assembly | EVT | 2024-04-20 | 2024-04-25 | PCB Fabrication | Factory A | FALSE
EVT Bring-up | EVT | 2024-05-01 | 2024-05-04 | SMT Assembly | EE Engineer A | FALSE
EVT Power Test | EVT | 2024-05-05 | 2024-05-15 | EVT Bring-up | EE Engineer A | FALSE
EVT Thermal Test | EVT | 2024-05-05 | 2024-05-15 | EVT Bring-up | ME Engineer B | FALSE
EVT Exit Review | EVT | 2024-05-20 | 2024-05-20 | EVT Power Test | PM | TRUE
DVT Design Fix | DVT | 2024-06-01 | 2024-06-09 | EVT Exit Review | EE Engineer A | FALSE
DVT PCB Layout | DVT | 2024-06-10 | 2024-06-30 | DVT Design Fix | Layout Team | FALSE
DVT SMT | DVT | 2024-07-01 | 2024-07-09 | DVT PCB Layout | Factory A | FALSE
DVT Functional Test | DVT | 2024-07-10 | 2024-07-25 | DVT SMT | EE Engineer A | FALSE
EMI Pre-test | DVT | 2024-07-10 | 2024-07-25 | DVT SMT | EMI Lab | FALSE
DVT Exit Review | DVT | 2024-07-30 | 2024-07-30 | DVT Functional Test | PM | TRUE
PVT Tooling Setup | PVT | 2024-08-01 | 2024-08-14 | DVT Exit Review | Tooling Dept | FALSE
PVT Pilot Run | PVT | 2024-08-15 | 2024-08-19 | PVT Tooling Setup | Factory A | FALSE
PVT Reliability Test | PVT | 2024-08-20 | 2024-08-30 | PVT Pilot Run | QA Team | FALSE
MP Start | MP | 2024-09-01 | 2024-09-01 | PVT Reliability Test | PM | TRUE