## Sheet1
Name | Stage | StartDate | EndDate | Dependencies | Resources | IsMilestone
Board Design | EVT | 2023-11-01 | 2023-11-14 |  | EE Engineer A | FALSE
Component Sourcing | EVT | 2023-11-01 | 2023-11-10 |  | Purchasing | FALSE
PCB Fabrication | EVT | 2023-11-15 | 2023-11-30 | Board Design | Vendor X | FALSE
Board Bring-up | EVT | 2023-12-01 | 2023-12-10 | PCB Fabrication | EE Engineer A | FALSE
EMI Testing | DVT | 2023-12-05 | 2023-12-15 | Board Bring-up | EE Engineer A | TRUE